## Sheet1
Story ID | Story Name | Description | Priority | Iteration (Sprint) number | Acceptance Criteria | Notes | Date started (actual date) | Date finished (actual date)
1 | Options of Soup | As a customer, I want to choose the soup of my single ramen, so that I can personalize my single ramen. | high | 1 | There are three options of soup for customers to choose. Customers must indicate a choice for soup. |  | 2020-03-23 | 2020-03-26
2 | Options of Noodles | As a customer, I want to choose the noodles of my single ramen, so that I can personalize my single ramen. | high | 1 | There are three options of noodles for customers to choose. Customers must indicate a choice for noodels. |  | 2020-03-23 | 2020-03-26
3 | Options of Spring onion | As a customer, I want to choose the spring onion of my single ramen, so that I can personalize my single ramen. | high | 1 | There are three options of spring onion for customers to choose. Customers must indicate a choice for spring onion. |  | 2020-03-23 | 2020-03-26
4 | Options of Nori | As a customer, I want to decide whether to have Nori in my single ramen, so that I can personalize my single ramen. | high | 1 | Customers can choose whether to have Nori in their fixed single ramen. Customers must indicate a choice for Nori. |  | 2020-03-23 | 2020-03-26
5 | Options of Chashu | As a customer, I want to decide whether to have Chashu in my single ramen, so that I can personalize my single ramen. | high | 1 | Customers can choose whether to have Chashu in their fixed single ramen. Customers must indicate a choice for Chshu. |  | 2020-03-23 | 2020-03-26
6 | Options of Boiled Egg | As a customer, I want to decide whether to have a boiled egg in my single ramen, so that I can personalize my single ramen. | high | 1 | Customers can choose whether to have a boiled egg in their fixed single ramen. Customers must indicate a choice for boiled egg. |  | 2020-03-23 | 2020-03-26
7 | Options of Spiciness | As a customer, I want to decide the level of spiciness, so that I can personalize my single ramen. | high | 1 | Customers can choose the level of spiciness of their fixed single ramen. There are six levels of spiciness(from 0 to 5) for customers to choose. Customers must indicate a choice for spiciness. |  | 2020-03-23 | 2020-03-26
8 | Items of a Fixed Ramen | As a customer, I want to all items of a fixed single ramen in a single page, so that I can submit my options of a fixed ramen in one go. | high | 1 | All fixed items and their options are shown on a single page. Customers can submit their options of a fixed ramen in one go. |  | 2020-03-23 | 2020-03-26
9 | Extra Nori | As a customer, I want to add extra Nori in my ramen, so that my ramen can taste better. | high | 1 | Customers can add extra Nori in their ramen. The number of extra Nori is optional. |  | 2020-03-27 | 2020-03-30
10 | Extra Boiled Egg | As a customer, I want to add extra boiled eggs in my ramen, so that my ramen can taste better. | high | 1 | Customers can add extra boiled eggs in their ramen. The number of boiled egg is optional. |  | 2020-03-27 | 2020-03-30
11 | Bamboo shooots | As a customer, I want to add bamboo shoots in my ramen, so that my ramen can taste better. | high | 1 | Customers can add bamboo shoots in their ramen. The number of bamboo shoots is optional. |  | 2020-03-27 | 2020-03-30
12 | Extra Chashu | As a customer, I want to add extra Chashu in my ramen, so that my ramen can taste better. | high | 1 | Customers can add extra Chashu in their ramen. The number of extra Chashu is optional. |  | 2020-03-27 | 2020-03-30
13 | Items of Add-ons | As a customer, I want to all items of add-ons in a single page, so that I can submit my options of add-ons in one go. | high | 1 | All add-ons are shown on a single page. Customers can submit their options of add-ons in one go. |  | 2020-03-27 | 2020-03-30
14 | Dining Options | As a customer, I want to choose eat in or take-away, so that I can decide whether eat in the restaurant according to its status. | high | 1 | Dining options are shown for customer to choose. Dining options are required. |  | 2020-03-27 | 2020-03-30
19 | Payment | As a customer, I want to know the amount of consumption intuitively, and choose my own payment method, cash or card, so that I can pay the bill with preferable method of payment except using the virtual stamps. | high | 1 | The system can list all the order choices and consumption amounts for customers to confirm. Customers can directly see the entrance of two payment methods, cash or bank card. |  | 2020-03-31 | 2020-04-02
16 | Register | As a customer, I want to register as a member, so that I can get a discount when the condition is met. | high | 2 | Customers must enter their fistname and surnaem, as well as at least one between email and mobile number to register. When the format of the user's email or mobile numver is incorrect, a popup dialog is shown to remind him/her and it cannot be registered. Upon registering successfully, customers can receive an email or SMS with 8-digit membership number. |  | 2020-04-06 | 2020-04-08
17 | Membership | As a customer, I want to choose whether to enter my membership number before choosing method of payment, so that I can choose whether to use the virtual stamps for this order. | high | 2 | Customers can easily enter their member ID before making payment. When the membership number entered is not vaild, the user should be prompted and he/she cannot pays using the virtual stamps. |  | 2020-04-08 | 2020-04-11
21 | Award | As a customer, I want get virtual stamp rewards when I use cash or bank card to pay successfully after joining the membership program, so that I can get a discount when my virtual stamp reach fixed number. | high | 2 | When customers successfully enter the membership number and successfully finish the payment,the system will add a virtual stamp in their accounts. If customers pay using virtual stamps, the system will set the number of virtual stamps in the user's account to 0. |  | 2020-04-08 | 2020-04-11
18 | Virtual Stamps | As a manager, I want that when the customer has already accumulated more than 10 virtual stamps, the fixed Ramen price is free and the number of virtual stamp is subtract to 10, so that I do not need to manually handle each incoming user request. | high | 2 | The corresponding member information from the local file can be found through the membership number, and obtain the number of virtual stamps. The system can correctly process the virtual stamp deduction and ensure the correct number of virtual stamps. When the number of virtual stamps does not reach 10, the user cannot pay using virtual stamps. |  | 2020-04-08 | 2020-04-13
20 | Bill | As a customer, I want to get a bill with relevant information after each purchase, so that I can keep vouchers for every purchase. | high | 2 | Regardless of whether the user uses cash, bank card or virtual stamp to pay, the system will provide a related ticket(i.e. a txt file). The bill should have the order number, the name of dishes, the flavor and add-ons, the amount of consumption, and other necessary relevant information. |  | 2020-04-12 | 2020-04-13
44 | a Fixed Ramen Price Modification | As a maneger, I want to modify the price of a fixed Ramen, so that I can expand sales and make a profit. | high | 2 | The price of a fixed Ramen can be changed when modified. The changed price is shown on menu. |  | 2020-04-14 | 2020-04-16
45 | Extra Nori Price Modification | As a maneger, I want to modify the price of extra Nori, so that I can expand sales and make a profit. | high | 2 | The price of extra Nori can be changed when modified. The changed price is shown on menu. |  | 2020-04-14 | 2020-04-16
46 | Extra Boiled Egg Price Modification | As a maneger, I want to modify the price of extra boiled egg, so that I can expand sales and make a profit. | high | 2 | The price of extra boiled egg can be changed when modified. The changed price is shown on menu. |  | 2020-04-14 | 2020-04-16
47 | Bamboo Shoots Price Modification | As a maneger, I want to modify the price of bamboo shoots, so that I can expand sales and make a profit. | high | 2 | The price of bamboo shoots can be changed when modified. The changed price is shown on menu. |  | 2020-04-14 | 2020-04-16
48 | Extra Chashu Price Modification | As a maneger, I want to modify the price of extra Chashu, so that I can expand sales and make a profit. | high | 2 | The price of extra Chashu can be changed when modified. The changed price is shown on menu. |  | 2020-04-14 | 2020-04-16
49 | Availability of Tonkostu Soup Modification | As a maneger, I want to modify the availability of Tonkostu soup, so that I can enable customer to know that Tonkostu soup has sold out. | high | 2 | The availability of Tonkostu soup can be changed when modified. When customers choose unavailable Tonkostu soup, a popup dialog is shown to prompt them. |  | 2020-04-14 | 2020-04-16
50 | Availability of Shoyu Soup Modification | As a maneger, I want to modify the availability of Shoyu soup, so that I can enable customer to know that Shoyu soup has sold out. | high | 2 | The availability of Shoyu soup can be changed when modified. When customers choose unavailable Shoyu soup, a popup dialog is shown to prompt them. |  | 2020-04-14 | 2020-04-16
51 | Availability of Shio Soup Modification | As a maneger, I want to modify the availability of Shio soup, so that I can enable customer to know that Shio soup has sold out. | high | 2 | The availability of Shio soup can be changed when modified. When customers choose unavailable Shio soup, a popup dialog is shown to prompt them. |  | 2020-04-14 | 2020-04-16
52 | Availability of Nori Modification | As a maneger, I want to modify the availability of Nori, so that I can enable customer to know that Nori has sold out. | high | 2 | The availability of Nori can be changed when modified. When customers choose unavailable Nori, a popup dialog is shown to prompt them. |  | 2020-04-14 | 2020-04-16
53 | Availability of Chashu Modification | As a maneger, I want to modify the availability of Chashu, so that I can enable customer to know that Chashu has sold out. | high | 2 | The availability of Chashu can be changed when modified. When customers choose unavailable Chashu, a popup dialog is shown to prompt them. |  | 2020-04-14 | 2020-04-16
54 | Availability of Boiled Egg Modification | As a maneger, I want to modify the availability of boiled egg, so that I can enable customer to know that boiled egg has sold out. | high | 2 | The availability of boiled egg can be changed when modified. When customers choose unavailable boiled egg, a popup dialog is shown to prompt them. |  | 2020-04-14 | 2020-04-16
55 | Availability of Bamboo Shoots Modification | As a maneger, I want to modify the availability of bamboo shoots, so that I can enable customer to know that bamboo shoots have sold out. | high | 2 | The availability of bamboo shoots can be changed when modified. When customers choose unavailable bamboo shoots, a popup dialog is shown to prompt them. |  | 2020-04-14 | 2020-04-16
27 | Soup Data | As a maneger, I want to view the number of each option of soup sold in last week, so that I can know customers' general taste for soup and adjust the business strategy. | high | 3 | The report about statistics of soup sold in the last week can be shown. |  | 2020-04-20 | 2020-04-25
28 | Noodles Data | As a maneger, I want to view the number of each option of noodles sold in last week, so that I can know customers' general taste for noodles and adjust the business strategy. | high | 3 | The report about statistics of noodles sold in the last week can be shown. |  | 2020-04-20 | 2020-04-25
29 | Spring Onion Data | As a maneger, I want to view the number of each option of spring onion sold in last week, so that I can know customers' general taste for noodles and adjust the business strategy. | high | 3 | The report about statistics of spring onion sold in the last week can be shown. |  | 2020-04-20 | 2020-04-25
30 | Spiciness Data | As a maneger, I want to view the amount of every spiciness level sold in last week, so that I can know customers' general taste for spiciness and adjust the business strategy. | high | 3 | The report about statistics of spiciness sold in the last week can be shown. |  | 2020-04-20 | 2020-04-25
31 | Nori Data | As a maneger, I want to view the number of Nori sold in last week, so that I can know customers' general taste for Nori and adjust the business strategy. | high | 3 | The report about statistics of Nori sold in the last week can be shown. |  | 2020-04-20 | 2020-04-25
32 | Chashu Data | As a maneger, I want to view the number of Chashu sold in last week, so that I can know customers' general taste for Chashu and adjust the business strategy. | high | 3 | The report about statistics of Chahu sold in the last week can be shown. |  | 2020-04-20 | 2020-04-25
33 | Boiled Egg Data | As a maneger, I want to view the number of boiled egg sold in last week, so that I can know customers' general taste for boiled egg and adjust the business strategy. | high | 3 | The report about statistics of boiled egg sold in the last week can be shown. |  | 2020-04-20 | 2020-04-25
34 | Extra Nori Data | As a maneger, I want to view the number of extra Nori sold in last week, so that I can know customers' general taste for extra Nori and adjust the business strategy. | high | 3 | The report about statistics of extra Nori sold in the last week can be shown. |  | 2020-04-20 | 2020-04-25
35 | Extra Boiled Egg Data | As a maneger, I want to view the number of extra boiled egg sold in last week, so that I can know customers' general taste for extra boiled egg and adjust the business strategy. | high | 3 | The report about statistics of boiled extra egg sold in the last week can be shown. |  | 2020-04-20 | 2020-04-25
36 | Bamboo Shoots Data | As a maneger, I want to view the number of bamboo shoots sold in last week, so that I can know customers' general taste for bamboo shoots and adjust the business strategy. | high | 3 | The report about statistics of bamboo shoots sold in the last week can be shown. |  | 2020-04-20 | 2020-04-25
37 | Extra Chashu Data | As a maneger, I want to view the number of extra Chashu sold in last week, so that I can know customers' general taste for extra Chashu and adjust the business strategy. | high | 3 | The report about statistics of extra Chashu sold in the last week can be shown. |  | 2020-04-20 | 2020-04-25
38 | Dining Options Data | As a maneger, I want to view the number of each option of dining in last week, so that I can know customers' general options for dining and adjust the business strategy. | high | 3 | The report about statistics of dining options in the last week can be shown. |  | 2020-04-20 | 2020-04-25
39 | Payment Data | As a maneger, I want to view the number of each option of methods of payment except virtual stamps in last week, so that I can know customers' general options for dining and adjust the business strategy. | high | 3 | The report about statistics of methods of payment in the last week can be shown. |  | 2020-04-20 | 2020-04-25
15 | View Availability | As a customer, I want to know whether an option is available when ordering, so that I can avoid ordering dishes that are not served actually. | high | 3 | The availability of each option should be shown on the menu. If an option is not available, customers cannot choose it or a popup dialog is shown. |  | 2020-05-06 | 2020-05-09
40 | Successful Registeration | As a customer, I want to receive detailed information printed on the bill after successful registration, so that I can avoid fault information. | medium | 3 | The registration details are printed in the ticket after successful registration. The membership information is written into file. |  | 2020-04-26 | 2020-04-27
22 | View Information | As a customer, I want to view individual membership information, so that I can identify myself. | medium | 3 | Customers have access to the personal information interface to view the information entered during registration. |  | 2020-04-28 | 2020-04-30
23 | Coupons Number | As a customer, I want to check the number of virtual stamps they have, so that I can make the plan to dine there next time. | medium | 3 | Customers can know the number of their virtual stamps after correctly entering their membership number. |  | 2020-04-28 | 2020-04-30
41 | Notify Change | As a customer, I want to be notified by SMS or email each time the number of virtual stamps changes, so that I can know the latest number of virtual stamps. | medium | 3 | After payment, the system queries the contact information of the customer. The system sends a message or mail to the customer. |  | 2020-04-28 | 2020-04-30
56 | Back to Fixed Ramen GUI | As a customer, I want that the user interface shows the items I have choosed, so that I can decide whether to change my options. | medium | 3 | When customers cliked the "Back" button, the selected options are shown in the fixed Ramen user interface. Even though customers do not make any change, "Next" button is available. |  | 2020-05-12 | 2020-05-14
57 | Back to Fixed Ramen GUI | As a customer, I want that the user interface shows the items I have choosed, so that I can decide whether to change my options. | medium | 3 | When customers cliked the "Back" button, the selected options are shown in the add-ons user interface. |  | 2020-05-12 | 2020-05-14
57 | Cancel the Order as a Member | As a customer, I want to cancel my order but my stamps do not be set, so that there is no loss when cancelling the order. | medium | 3 | When customers cliked the "Cancel" button, the number of collected stamps does not be subtracted 10. |  | 2020-05-12 | 2020-05-14
57 | Choose Stamps Use | As a customer, I want to choose whether to use my stamps to get a discount, so that I can make my choices according to my individual situation. | medium | 3 | When the number of virtual stamps is more than or equal to 10, a popup dialog is shown to ask customers about stamps use. If customers do not chooose using stamps, they can pay the bill as usual and get a stamps when successful payment. |  | 2020-05-12 | 2020-05-14
42 | Visualization | As a manager, I want to make the system generate a graph report weekly, describe all the amount data in visualized way, so that I can get information intuitively and quickly adjust the business strategy. | medium | 4 | Result shown must be raw data, with no modification. |  | 2020-04-20 | 2020-04-25
24 | View Membership Information | As a manager, I want to view the membership information, so that I can adjust business practices. | medium | 4 | The manager has access to the information of members，including the number of members and their virutal stamps. |  | 2020-05-04 | 2020-05-05
26 | More Dishes | As a customer, I want to purchase more than one dish in one order, so that I can complete the payment conveniently. | low | 4 | Customers are allowed to more than one dish in one order. Selected dishes are shown in one ticket. |  | 2020-05-06 | 2020-05-09
25 | Modify Individual Information | As a customer, I want to modify individual membership information, so that I can get information from restaurant in time. | low | 4 | Customers can change their personal information after successfully entering membedship number. |  | 2020-05-10 | 2020-05-11
43 | Data Report Email | As a customer, I want to receive the report in my email every Monday after subscribing, so that I can get flavor changes information timely. | low | 4 | Report email must be delivered on Monday every week. |  | 2020-05-12 | 2020-05-14